- Scope

This procedure applies to the planning function for all forest operations.

- Objective

The objective of forest planning is to ensure that all planning activities are fully integrated regarding the various times scales, between harvesting and silviculture operations, and other planning activities relating to managing the forest resource.

- Legal Compliance Requirements

Field operations shall comply with all national laws and codes of practice.  Where no such code exists, the operation shall comply with the “ILO - Code of Practice on Safety and Health in Forestry” and IFC Standards.

- Operational Control

| 1 | Refer to the Preventative Action, Corrective Action procedures, and CAR Form where non-compliances to this prescription are observed. | Q |
| --- | --- | --- |

  - Generic Forest Planning Prescriptions

| 1 | The company shall use 4 distinct levels of planning to ensure that logs are delivered in full, on time and within specification: - Long term fibre plan - Tactical planning - Annual planning - Operational planning | SPEQ |
| --- | --- | --- |
| 2 | All levels of planning shall consider the type of management systems to be used for managing forest growth and harvesting systems to be used, based on the ecology of the forest. | SPEQ |
| 3 | Inventories shall be done prior to harvesting operations, and then at regular intervals to determine growth rates of the forest, and the sustainable yield of the forest. | PEQ |
| 4 | Where necessary plans shall reflect changes to ensure the continued sustainability of the forest based on the most recent inventory results | PEQ |
| 5 | Rationale for species selection and rates of annual harvest shall be based on the results of these inventories. | PEQ |
| 6 | Forest Management Prescriptions shall detail the management systems to be used based on the restrictions of the various systems given in the BOPs and the results of the harvest systems analysis for the company – see 4.2.1 below. | PEQ |
| 7 | Forest growth, species composition and forest dynamics shall be regularly monitored through inventories. | PEQ |
| 8 | Refer to the Conservation Management and Land Cover classification FMP’s in regards to : - The identification and protection of rare threatened and endangered species, and - Mapping of forest resources. | EQ |
| 9 | Planning is also focussed on ensuring that the environmental and social objectives of the company are met. | SE |
| 10 | Each Plantation shall complete a Plantation Management Plan (PMP) following the format in the template, and this shall be updated at least once every 5 years. | Q |
| 11 | Planning shall be completed as per company requirements: - Tactical harvest plan – 3 - 5 year period and rolled over annually - Roads plan – annually - APO – annually - Operational harvest and silviculture plans – >2 weeks prior to harvesting/planting | SPEQ |
| 12 | The Tactical Harvesting Plan shall be included in the Plantation Management Plan (PMP). | SPEQ |
| 13 | The long term fibre plan lays the basis for tactical planning | SPEQ |
| 14 | The long term fibre plan shall be updated yearly or after a major (bigger than 50Ha) disaster due to disease or fire damage. | SPEQ |
| 15 | The long term harvesting scheduling shall be based on the sustainable clearfell volumes, thinning schedules and market requirements. | PQ |
| 16 | The schedule shall be created using the Microforest Harvest Scheduling System (HSS) and once balanced and provisionally approved, the felling dates from the relevant exercise will be written back into Microforest PMi, updating the “Fell date” field in the compartment view. | PQ |
| 17 | Outputs shall include: Sustainable clearfell volume graphs and statistics; long term product spread; long term weeding, planting and pruning plan schedules. These shall be included in the Growing Stock Management Plan (GSMP). | PQ |
| 18 | The long term plan detail shall span two rotations: Next financial year + > 19 years for Euc and next financial year + 35 years for pine. | PQ |
| 19 | The long term plan shall be summarised in a Growing Stock Management Plan that will be updated annually. | PQ |
| 20 | The Tactical Plan shall be summarised in a Tactical Harvesting Plan that will be updated annually and included in the Plantation Management Plan (PMP). | PQ |
| 21 | Where it is necessary to make changes to the Microforest data base a Change of Status Form shall be completed and submitted to the Planning Office. This form shall be signed off by the Plantation Manager and Planning Forester responsible for the plantation in question before any changes will be affected in MicroForest. | Q |

  - Sustainable Yield Methodology

    - (Uganda)

| 1 | Annual Sustainable Cut for each Working Circle and growing regime and fell year shall be determined in Microforest HSS | QP |
| --- | --- | --- |
| 2 | A long term plan with a minimum clearfell age of the following shall be “run” in HSS: - 10 Years for Eucalyptus Pole Regime – Sawtimber is seen as a secondary product from the pole regime. Should Sawtimber become a primary product, pole compartments will receive a second thinning and be converted to a sawtimber regime. The minimum Fell Age will be set to ‘8.5’ in HSS and the maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. - 18 Years for Pine Sawtimber Regime. The maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. Pine shall be harvested on a minimum diameter basis as well as a minimum Fell Age. During the HSS run, attention shall be given to ensure that the Age Class Distribution does not drop below 16 years for any given year. | QP |
| 3 | The outcome of this “run” should be a maximum allowable cut per felling year, which has to be normalized (this to happen in MF Tactical Planning System [TPS]). Felling dates shall be written back to Microforest PMi | QP |
| 4 | Once yearly a 3 - 5 year tactical plan shall be created using the felling dates from HSS. If compartment clearfell dates are changed via the Tactical Planning System, the HSS long-term volumes will need to be re-run to determine the long-term impact of such changes. | QP |
| 5 | The tactical plan shall be optimized in terms of allowable cut, harvest logistics and product balancing. No optimization on compartments not falling in the 5 year tactical plan period unless for specific reasons such as compartment consolidation. These changes must be approved by the HoP. | QP |
| 6 | Due to the unique situation in Uganda, where there is a big variance in planting areas per year per plantation, annual sustainable cut calculations shall be done by grouping the three plantations together and not on a plantation per plantation basis in order to maximise the volume that can be harvested for the country. | QP |

    - (Tanzania)

| 1 | Annual Sustainable Cut for each working circle and growing regime and fell year shall be determined in Microforest HSS | QP |
| --- | --- | --- |
| 2 | A long term plan with a minimum clear fell age of the following shall be “run” in HSS: - 10 Years for Eucalyptus Pole Regime. Sawtimber is seen as a secondary product from the pole regime. Should Sawtimber become a primary product, pole compartments will receive a second thinning and be converted to a sawtimber regime. The minimum Fell Age will be set to ‘10’ in HSS and the maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. - 18 Years for Pine Saw timber Regime - The maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. Pine shall be harvested on a minimum diameter basis as well as a minimum Fell Age. During the HSS run, attention shall be given to ensure that the Age Class Distribution does not drop below 16 years for any given year. | QP |
| 3 | The outcome of this “run” should be a maximum allowable cut per felling year, which has to be normalized (this to happen in MF Tactical planning system). Felling dates shall be written back to Microforest PMi | QP |
| 4 | Once yearly a 5 year tactical plan shall be created using the written back felling dates from HSS. This to start 5 years before first clear fell to commence. If compartment clearfell dates are changed via the Tactical Planning System, the HSS long-term volumes will need to be re-run to determine the long-term impact of such changes. | QP |
| 5 | The tactical plan shall be optimized in terms of allowable cut, harvest logistics and product balancing. No optimization on compartments not falling in the 5 year tactical plan period unless for specific reasons such as compartment consolidation. These changes must be approved by the HoP. | QP |

    - (Rwanda)

| 1 | Annual Sustainable Cut for each growing regime and fell year shall be determined in Microforest HSS. | QP |
| --- | --- | --- |
| 2 | A long term plan with a minimum clear fell age of the following shall be “run” in HSS: - Due to the unique age class and geographical distribution of the Rwanda growing stock, compartments shall be scheduled on a Block basis and according to market requirements. The initial scheduling will be done to meet machine and market capabilities. - 12 Years for Eucalyptus Pole Regime for all new establishment. Sawtimber is seen as a secondary product from the pole regime. Should Sawtimber become a primary product, pole compartments will receive a second thinning and be converted to a sawtimber regime. The minimum Fell Age will be set to ‘10’ in HSS and the maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. - 18 Years for Pine Saw timber Regime for all new establishment. The minimum Fell Age will be set to ‘16’ in HSS and the maximum Fell Output shall not exceed the long-term sustainable yield. These figures will be updated annually. | QP |
| 3 | The outcome of this “run” should be a maximum allowable cut per felling year, which has to be normalized (this to happen in MF Tactical planning system). Felling dates shall be written back to Microforest PMi. | QP |
| 4 | Once yearly a 5 year tactical plan shall be created using the written back felling dates from HSS. This to start 5 years before first clear fell to commence. If compartment clearfell dates are changed via the Tactical Planning System, the the HSS long-term volumes will need to be re-run to determine the long-term impact of such changes. | QP |
| 5 | The tactical plan shall be optimized in terms of allowable cut, harvest logistics and product balancing. No optimization on compartments not falling in the 5 year tactical plan period unless for specific reasons such as compartment consolidation. These changes must be approved by the HoP. | QP |

  - Tactical Harvesting Plan (THP) Prescriptions

| 1 | The tactical plan is compiled within the strategic objectives set for the company, and shall be based on the schedules from the long term harvesting, next 5 year’s market requirements, machine and processing constraints and other harvesting variables. | SPEQ |
| --- | --- | --- |
| 2 | The aim of the tactical plan is to match and describe the most appropriate equipment and harvesting techniques with the terrain and site conditions for an area designated for harvesting. | SPEQ |
| 3 | Additionally, the market existing within the time frame will dictate the products to be produced, which influences the type of harvesting and transport systems. | Q |
| 4 | The useful life of the equipment indicates the length that the plan needs to be prepared for. | P |
| 5 | Based on the results of the evaluation, alternative systems shall be approved and used, which ensure that selected systems cover all site and terrain conditions. | SPEQ |
| 6 | The tactical harvest plan shall be completed as defined in the Tactical Harvest Planning BOP | SPEQ |
| 7 | The tactical plan shall be updated annually in March or after a major (bigger than 50Ha) disaster due to disease or fire damage. | SPEQ |
| 8 | The plan shall be created and balanced using the Microforest Tactical Planning System (TPS). | Q |
| 9 | The plan shall be housed in Microforest Tactical Planning module. | Q |
| 10 | The next financial year’s clearfell and thinning APO shall be housed in the Tactical Planning module and the fell dates for the next financial year shall be written back and “locked” in Microforest PMi compartment view. | Q |
| 11 | Only on authorization from HOF and HOP shall a felling date for the signed off next financial year’s compartments be unlocked / any new compartment added. | Q |
| 12 | Both six months and one month before the end of the relevant financial year, the PM’s shall submit the APO compartments that will not be felled / thinned in the APO year to the planning department for rescheduling. This refers specifically to carry over clearfelling and thinning compartments. Clearfell dates and thinning ages shall be updated in MicroForest PMi by the relevant Forest Planner. | Q |
| 13 | Outputs shall include: Product statistics; APO volumes and compartments; Critical roads and routes; Harvesting system / team utilization in the form of a Tactical Harvest Plan. | Q |
| 14 | A 3- 5 year tactical harvesting and thinning map shall be supplied by the planning department for each plantation. | PQ |

  - Tactical Silviculture Plan (TSP) Prescriptions

| 1 | The compartments harvested in a particular year forms the bulk of all new plantings. Including any new areas or any still unplanted areas on the management unit. | SPEQ |
| --- | --- | --- |
| 2 | The THP in conjunction with the financial model (new planting areas) is a good indicator of the compartments and new areas earmarked for planting in the next 3 – 5 years. | SPEQ |
| 3 | Where there is a necessity to consider medium term planting compartments or crop fail compartments, the THP in conjunction with the financial model (new planting areas) should be used to obtain the information. | SPEQ |
| 4 | A planting map shall be supplied for all compartments to be planted by the planning department. These are to be used for establishment planning and operations and must accompany the Establishment Assessment Form. | PQ |
| 5 | The long-term harvesting plan shall provide the input to long-term silviculture planning in terms of seed and seedling requirements. This will be available in the form of a Growing Stock Management Plan. | PQ |
| 6 | No additional Tactical Silviculture Plan is required to meet the objectives of the company. | SPEQ |
| 7 | As a company we are committed to reforestation in a timely fashion. Our metric to assure this is to not exceed a maximum of 10% TUP at any one time, or meeting regulatory requirements. | PEQ |

  - Roads Plan Prescriptions (annual)

| 1 | The tactical roads plan, which flows from the tactical harvest plan, is usually completed for a 3 – 5 year period. | SPEQ |
| --- | --- | --- |
| 2 | The roads plan considers the requirements of the road categories that the company adheres to, for road infrastructure development. | SPEQ |
| 3 | The compartments in the THP, identified for harvesting for the following year, indicates which roads are primarily required for construction/upgrading in the roads plan. | SPEQ |
| 4 | The roads plan shall be completed as defined in the Roads Planning BOP. | SPEQ |
| 5 | A 3-5 year roads upgrading and maintenance plan shall be supplied by the planning department for each plantation. This map will form part of the tactical harvesting map. | PQ |
| 6 | Individual road segments require a unique name, LID number and buffer width. Road segments shall be named based on the adjacent compartment names. | PQ |
| 7 | Routes names shall be assigned based on the current NFC road naming system of using the main route number followed by an odd (left) or even (right) number determined by the direction of the sub-route from the main route. Additional sub-routes shall comply with this naming system. | PQ |
| 8 | Routes shall be compiled from the relevant road segments names in the TPS in PMi. | PQ |

  - Operational Harvest Planning (OHP) Prescriptions

| 1 | Annually, by the end of May, each Harvesting Manager shall supply the HoF and HoP with a detailed Annual Operational Harvesting Plan for the first year of the updated Tactical Plan. | SPEQ |
| --- | --- | --- |
| 2 | Compartment level operational planning is completed for each compartment, at least two weeks (14 days) before harvesting operations commence. | PQ |
| 3 | The objective of the compartment level OHP is to refine the information in the THP and the annual OHP, to ensure that harvesting operations can be completed in full, on time and within specifications. | PQ |
| 4 | The compartment level OHP considers the environmental and social objectives of the company. | SE |
|  | The compartment level OHP shall be completed as defined in the OHP BOP | SPEQ |

  - Operational Silviculture Planning (OSP) Prescriptions

| 1 | Compartment level operational planning is completed for each compartment, at least the week before silviculture operations commence. | SPEQ |
| --- | --- | --- |
| 2 | The objective of the compartment level OSP is to refine the information in the APO, to ensure that silviculture operations can be completed in full, on time and within specifications. | SPEQ |
| 3 | The compartment level OSP considers the environmental and social objectives of the company. | SE |
| 4 | The compartment level OSP shall comply with the prescriptions given in the Silviculture Planning FMP | Q |
| 5 | The compartment level OSP shall be completed as defined in the OSP FMP/BOP | SPEQ |

  - Fire Management Planning Prescriptions (annual)

| 1 | A Fire Management Plan shall be done for each forest. | SPEQ |
| --- | --- | --- |
| 2 | This fire management plan shall be updated annually in July and shall be accompanied by a Fire Risk Rating Map to be supplied by the Planning Department. | SPEQ |
| 3 | The Fire Risk Rating shall also be updated for each compartment on MicroForest PMi. | SPEQ |

  - Open Area (natural area) Planning Prescriptions

| 1 | Refer to the Conservation Management MP for details on tactical and annual Open Area management planning. | SPEQ |
| --- | --- | --- |

  - Responsibility Levels

| 1 | The planning department shall be responsible for the creation and update of Long term and Tactical plans. | Q |
| --- | --- | --- |
| 2 | On completion of these plans they shall be signed off: - Long term plan: Group Chief Executive Officer (GCEO), Head of Planning and Head of Forestry, and - Tactical Plan: GCEO, Head of Planning, Head of Forestry, Country CEO and Country Forestry Manager. | Q |
| 3 | Operations shall be responsible for the creation and updating on annual and operational plans. | Q |
| 4 | The Plantation Manager shall be responsible for updating, signing and dating the most up to date version of the Plantation Management Plan. An unsigned copy shall be stored on the IMS, with a copy of the signed front page being held in file on the relevant plantation. | Q |
| 5 | Annual Plans shall be signed off by the Country Forestry Manager | Q |

- Responsibility

The following positions are responsible for ensuring compliance with this procedure:

| Superior Second Level: | HEAD OF PLANNING |
| --- | --- |
| Superior First Level: | FORESTRY MANAGER |
| This Position: | PLANTATION MANAGER |

- Appendix

- Records

| Record | Responsibility | Where kept | Retention |
| --- | --- | --- | --- |
| Long term fibre plan | Head of Planning | Head office | 5 years |
| Tactical harvest plan | Harvesting manager | Plantation/District Office | 5 years |
| Annual roads plan | Forestry manager | Plantation/District Office | 5 years |
| Annual plan of operations | Plantation manager | Plantation/District Office | 5 years |
| Operational Harvest Plan | Harvesting Forester | Plantation/District Office | 5 years |
| Operational Silviculture Plan | Silviculture Forester | Plantation/District Office | 5 years |
| Compartment Plan (Map) | Harvesting Forester | Plantation/District Office | 5 years |
| Forest Management Database | Head of Planning | Head Office | Indefinite |
| Change of status Forms | Head of Planning | Head Office | 5 years |

- References

| IMS Manual | OHSAS 18001:2007 | ISO 14001:2004 | ISO 9001:2000 |
| --- | --- | --- | --- |
| 3.2 | 4.3.1 | 4.3.1 | 5.2; 7.2.1; 7.2.2 |
| FSC | NOSA 2008 | Aspect /Impact/Hazard Register | BOP |
| 4.4; 5.1; 5.6; 7.1; 7.2; 7.3; 7.4 | 3.01 | Impacts Risks |  |

- Definitions